## Slide 1: RIVERWOODS INVESTMENT READINESS PIONEERS
Checklist for Delivery
Pandora Ellis & Rachel Nixseaman
Pandora Ellis & Rachel Nixseaman

## Slide 2: Introduction
Here we have broken down the typical phases of a participatory project, and added the checklists that we find helpful to work through when we are designing a process. We find this particularly helpful to use alongside the toolkit of templates.
While not all of these lists will be relevant for your project, we hope that this is a useful tool while you design successful projects.
Pandora Ellis & Rachel Nixseaman

## Slide 3: Inception & Planning
Define purpose and aims of the project
Identify meaningful opportunities for community participation
Identify target groups (See Stakeholder Mapping Template and Sector Mapping Template)
  Explore potential barriers to engagement as well as solutions before delivery commences
  Identify relevant networks to engage with
Agree scope of project: what is or isn’t in scope (See Scoping Template and Project Definition Template)
Agree timeline and clear milestones for delivery success (See Project Phases Template)
Agree delivery team roles and responsibilities (See Project Governance Template)
  Consider requirements such as data handling, risk management, protection officer, etc.
Pandora Ellis & Rachel Nixseaman

## Slide 4: Communications
  Create accessible communications package
    Ensure accessibility for diverse participant needs (consider age, disability, access to internet, etc.)
    Consider online and offline communications
    Share comms through relevant community and cross-sector networks
  Plan communications calendar
    Consider milestone events/activities and how much notice might need to be given
    Plan which channels to use (social media, local radio, mailing lists, etc.)
  Consider how you will share outcomes
Pandora Ellis & Rachel Nixseaman

## Slide 5: Participant Journey
  Consider the stages that a participant will progress through and the processes they might engage in
    Draft a timeline of milestones and outcomes to share with participants
    Create a storyboard of a hypothetical participant journey to clearly communicate participation and expectations (See Project Journey Templates)
  Identify potential barriers to engagement
    Consider accessibility (both in-person and online), additional support needs, financial constraints, time commitment, etc.
    Mitigate barriers as much as possible, setting aside funds to provide personalised support where necessary (e.g. translators, travel costs)
Pandora Ellis & Rachel Nixseaman

## Slide 6: Project Delivery
  Plan engagement sessions based on the participant journey, but be willing to be flexible and adapt!
    Plan sessions to meet the needs of participants (information sharing, access to resources, tools, etc.)
    Include space for participants to feed back and shape future sessions
  Provide tailored support where possible, including a mechanism to request this support
  Consider how best to be transparent about process and outcomes
    Communicate outputs with participants as well as intended actions
    Share design and learning with delivery partners and stakeholders
Pandora Ellis & Rachel Nixseaman

## Slide 7: Monitoring, Evaluation & Reporting
  Schedule regular delivery team check-ins throughout the process (See Reflections Template)
  Schedule learning and feedback sessions
    Internal sessions for delivery team to review delivery, roles and responsibilities
    External sessions to gather feedback and learning from participants
  Gather qualitative and quantitative feedback
    Record numbers of participants engaging at each stage
    Gather case studies where possible (interviews, feedback forms, surveys)
  Share your learning
Pandora Ellis & Rachel Nixseaman